## Overview
Fairlane — Phase 2 Mini-Project Breakdown
Each team member's task treated as its own mini-project with objectives, approach, dependencies, and outcome
# | Mini-Project | Owner | One-line Summary
1 | Database & Scheduler Core | Vansh Sagar | Design the schema and build a safe, working FCFS + Priority-with-Aging scheduler.
2 | NFS Setup | Harshvardhan Sharma | Establish shared storage with per-user isolation and a common Python environment.
3 | Remote Execution Launcher, Training Script & GPU Verification | Suryansh Bhatnagar | Build the Worker Agent and prove GPU-targeted, memory-aware job execution works.
4 | Dashboard, API & Overall Look/Feel | Vansh Garg | Build the API layer, dashboard, and explore UI/UX to make the system user-friendly.

## MP1 - Vansh Sagar
Mini-Project 1: Database & Scheduler Core
Owner: Vansh Sagar
Objectives
• Design a normalized PostgreSQL schema covering users, jobs, executions, workers, queues, and logs.
• Implement FCFS and Priority-with-Aging scheduling logic.
• Guarantee no job is ever assigned to two workers at once, using transactions and row-level locking.
• Define and agree with Suryansh on the exact dispatch and completion-callback data contract, so the Scheduler and Worker Agent can be connected later with minimal rework.
Suggested Approach
• Start with a minimal schema (USER, JOB, WORKER) and a basic FCFS loop before adding priority/aging.
• Implement SELECT ... FOR UPDATE inside a transaction for job assignment.
• Add the effective_priority formula once FCFS is proven to work correctly.
• Test correctness by simulating two scheduler runs firing at the same time.
• Write down the dispatch request format (job_id, script_path, gpu_index) and the completion callback format (job_id, exit_code, log_path) before either side starts building against it.
Dependencies
• None required to start — this is the foundational module everyone else builds against.
• Will need to confirm the shared folder path convention with Harshvardhan once script paths need to be stored/validated.
Outcome
A working scheduler that reliably picks the next job, locks it, and assigns it to a worker — provably safe under concurrent access, with a documented interface ready for the Worker Agent to plug into.

## MP2 - Harshvardhan
Mini-Project 2: NFS Setup
Owner: Harshvardhan Sharma
Objectives
• Establish a shared folder accessible from multiple machines.
• Enforce per-user file isolation using standard Unix/NFS permissions.
• Check whether a common, shared Python environment (with all required dependencies) can be stored directly on the NFS server and used by every machine — since we are not currently implementing per-user or per-job dependency isolation.
• Produce a documented, repeatable setup process for future machines joining the system.
• Share the finalized folder structure/path convention with Vansh Garg and Vansh Sagar so job paths are stored and requested consistently.
Suggested Approach
• Set up one machine as the NFS server, export a shared folder.
• Mount that folder as a client on at least two other machines.
• Create matching UIDs across machines, a compute_workers group, and apply 750 permissions per user folder.
• Test isolation by confirming one user cannot access another's folder, while a worker-owned account can still read scripts to execute them.
• Create a single shared Python virtual environment (with PyTorch and other common dependencies) inside the NFS folder, and test whether multiple machines can activate and use it directly over NFS without installing anything locally.
Dependencies
• None required to start — this module can be built independently.
• Should confirm with Suryansh what folder/file layout his launcher expects (e.g. where logs should be written), and what dependencies his training script actually needs, before finalizing the shared environment.
Outcome
A working shared-storage layer where users can place scripts/data and workers can read them, with real per-user isolation — plus confirmation of whether one common shared Python environment on NFS is a viable approach, directly validating our stated assumption that all workers share an identical, pre-configured environment.

## MP3 - Suryansh
Mini-Project 3: Remote Execution Launcher, Training Script & GPU Verification
Owner: Suryansh Bhatnagar
Objectives
• Build a working Worker Agent that can receive a dispatch request and execute a job accordingly.
• Prove that a Python training script can be launched on a specific, targeted GPU on a remote machine.
• Confirm that CUDA_VISIBLE_DEVICES genuinely restricts a script to seeing only its assigned GPU (or CPU), and that it cannot see or access any other GPU on the machine.
• Test running multiple scripts on the same GPU simultaneously, sharing its limited memory, to validate our multi-job-per-GPU design.
• Check a GPU's live usage and free memory before assigning a job to it — reject the assignment if the GPU is already under heavy load, or if its free memory is lower than what the job requires.
• Capture the job's output and completion status.
• Define and agree with Vansh Sagar on the exact dispatch and completion-callback data contract, so the Worker Agent and Scheduler can be connected later with minimal rework.
Suggested Approach
• Write a simple PyTorch script (e.g. a small CNN trained on MNIST).
• Build a launcher that sets CUDA_VISIBLE_DEVICES to a chosen GPU index and starts the script via subprocess.Popen().
• Verify isolation: from inside the running script, confirm only the assigned GPU is visible (e.g. check torch.cuda.device_count() reports 1, not the machine's true GPU count).
• Run two or more scripts on the same GPU at once, watching whether both fit within its total memory, and observe what happens if they don't.
• Use NVML to read a GPU's current utilization percentage and free memory before launching a job, and only proceed if both checks pass.
• Redirect stdout/stderr to a log file, and check the exit code once each process finishes.
• Build the Worker Agent's dispatch-receiving endpoint to match the agreed contract with Vansh Sagar, and test it independently using a manually simulated dispatch request (e.g. via curl) before the real scheduler exists.
Dependencies
• Needs the shared folder path/structure from Harshvardhan, so the launcher reads scripts from the correct location.
• Needs the agreed dispatch/callback data contract from Vansh Sagar before finalizing his endpoint's request/response shape.
Outcome
A standalone, working prototype confirming: GPU isolation via CUDA_VISIBLE_DEVICES works correctly, multiple jobs can safely share one GPU's memory when there's enough room, and a live usage/memory check can correctly decide whether a new job should be assigned to a given GPU — built against a documented interface, ready to be wired directly into the real Scheduler once both are complete.

## MP4 - Vansh Garg
Mini-Project 4: Dashboard, API & Overall Look/Feel
Owner: Vansh Garg
Objectives
• Provide a working API layer for submitting jobs and checking status.
• Give users a clear, simple way to see their job's state.
• Establish a consistent visual identity for the whole project.
• Explore UI/UX designs and application features to make the system more user-friendly and visually appealing.
• Agree with Vansh Sagar on the exact field names/types for job submission, job status, and worker registration payloads.
• Agree with Harshvardhan on the shared-folder path convention, so the job submission form requests the correct script path format.
• Use the same job/worker state names defined in the scheduler's design (QUEUED/RUNNING/etc., ONLINE/DRAINING/etc.) for consistent status display.
Suggested Approach
• Before writing endpoint code, confirm the shared field names/state names with the other three, and build initial mock/sample data using those same names.
• Build FastAPI endpoints for job submission, status lookup, and worker registration against that agreed shape.
• Research existing dashboards/schedulers (e.g. Run:ai's UI, Slurm web interfaces) for inspiration on layout and features worth adopting.
• Sketch a few UI/UX design options (e.g. wireframes or mockups) for the job submission form and status view before committing to one.
• Design a simple dashboard UI showing job status, using the confirmed state names.
• Define a consistent color scheme, typography, and layout style to apply across all future screens.
Dependencies
• Needs the schema field names and job/worker state names from Vansh Sagar.
• Needs the shared folder path convention from Harshvardhan.
• Needs the worker registration payload shape from Suryansh, once his Worker Agent's startup behavior is defined.
Outcome
A functioning API + dashboard shell, built against the same data contract as the Scheduler, Worker Agent, and NFS layer — so wiring everything together later requires minimal rework — plus a visual style guide and a set of explored UI/UX design directions the whole project can follow going forward.